ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	3

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & Period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	6

6.3.	Facilities to be provided by the Contractor	6

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	7

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Albania

## Contracting authority

University ‘‘Eqrem Çabej’’, Gjirokaster

## Country background

Albania has a population of 2.87 Million inhabitants, a life expectancy at birth at 78.2 years and a GDP per capita at 4,544 USD. After the fall of communism went through a process of transition from a centralized economy to a market-based economy on the principles of the free market and has made remarkable economic progress during these past three decades. Due to strong growth performance, Albania grew from one of the poorest nations in Europe to a middle-income country, with poverty declining by half during that period.

Albania is categorized as an upper-middle income country with an economy mostly based on the service sector (54.1%) while the agriculture (21.7%) and industrial sector (24.2%) account less than half.

However, the global financial crisis exposed the weaknesses of Albania’s growth model and highlighted the need to shift from consumption-fueled to investment- and export-led growth. The new model will need to help those people with less access to economic opportunities to contribute to, and benefit from, economic growth.

In order to accelerate the pace of equitable growth, Albania is implementing structural reforms that will raise productivity and competitiveness in the economy, create more jobs, and improve governance and public service delivery. Enhanced regional connectivity and access to regional and global markets, coupled with export and market diversification, can also help promote faster growth.

Significant progress, propelled by the ongoing reforms, has created the conditions for rebounding business confidence and domestic demand, including early signs of increased investment..

## Current situation in the sector

The Greece Albania CB area presents a unique opportunity for the implementation of sustainable new development models that will incorporate its regional geographic position, the richness of natural endowments, the significant number of elements of cultural & historical heritage, as well as its vibrant folklore.

However, the tourism sector related activities are not a major economic activity in a large part of the CB area, especially in the inland rural part. As a result, despite the presence of abundant natural environment potential, the tourism industry has yet to become a major development driver, thus not providing a stable or self-reliant source of income for the local population and business people. In the cultural aspect of the area, it is clear that for the regions of Epirus (Ioannina & Arta Regional Units) and Gjirokastër County livestock herding and the production of dairy products, most notably cheese, milk and yoghurt, are an integral part of local culture and culinary tradition.

However, in more recent times the decline in the population occupied with small scale primary sector activities and the increased commercialization of production threatens the artisanal forms of the said activities and the local traditions connected to it..

## Related programmes and other donor activities

The below mentioned  projects are co-financed by the European Union, in accordance with the rules of  IPA Cross Border Programme Greece – Albania:

- INECO “Innovative Economy Ecosystem”,Subsidy Contract A2-2.2.-4 under the INTERREG IPA CBC PROGRAMME "GREECE-ALBANIA 2014-2020"

- VirtuaLand: “ An Immersive Virtual Experience for Cultural and Natural Heritage Sites ” Subsidy Contract <A4-2.1-20>  under the INTERREG IPA CBC PROGRAMME

- STONE.ART “Thematic Tourism Development Through The Preservation of Stone” Subsidy Contract <A4-2.1-18>  under the INTERREG IPA CBC PROGRAMME.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project is to preserve the local culinary tradition in cheese making, to further integrate it to local innovative development approaches and to improve the quality and competitiveness in tourism and culinary sectors in the CB areas of Albania and Greece. The project has the following specific objectives:

•	Protecting, branding & promoting in internal and international markets of traditional cheese products as well as other related gastronomic products of the region;

•	Defining and promoting the innovative Cheese Route as a joint tourism product;

•	Innovative Training activities for improving the capacities of the local stakeholders in the tourism sector and implementation of pilot actions for the establishment of the Cheese Route at the CB area as a cultural/ tourism asset.

The project aims to serve the above by diagnosing local dairy value chains to map and eventually create a transnational Cheese Route between the project areas, including various thematic sub-routes. Participation in the Cheese Route will be subject to an established set of criteria, defined by the partners in accordance with the appropriate legislation.

## Purpose

The purpose of this contract is as follows:

To support the contracting authority to contribute to the achievement of the project’s objectives and results and specifically:

- the implementation of Project Management and Co-ordination activities, (WP1)

- the preparation of a study on “Diagnosis Study of sectors Linkage at Regional Level”. (WP3)

- the development of a Local Action Plan for Agro and Rural Tourism. (WP5)

- the development of Cheese Agri – tourism network and Project External Evaluation. (WP5)

## Results to be achieved by the contractor

Based on the deliverables and specific work to be carried out the results to be achieved by the contractor are the following:

- Successful project management.

- Successful technical support, including the elaboration of high-quality reports, studies, guidelines etc.

In specific,

  - Successful project management support and submission of the necessary reports.

  - Elaboration of the 1st study “Diagnosis Study of sectors Linkage at Regional Level”.

  - Development of a Local Action Plan for Agro and Rural Tourism.

  - Development of Cheese Agri – tourism network and Project External Evaluation.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The main assumptions underlying the project are the following:

•	The consultant/s is/are well informed and experienced on his/her role for the successful realization of the project.

•	The actions foreseen are closely related to every-day functions and aims for the efficacious implementation of the project.

•	The time schedule will correspond to the financial resources and their distribution.

•	During the planning the responsibilities of the consultant will be allocated strictly and clearly.

•	The actions, researches, audio/photo/questionnaires and information provided to the community will consider the publicity rules of the Interreg IPA CBC Greece-Albania 2014-2020 Programme and CheeseCulT Communication Strategy developed according to the EU guidelines Communication and University internal procedure and will promote the role of the European Union, in conjunction with the project’s strategy, outcomes and results in the target areas.

•	Excellent and effective cooperation and interaction between collaborators and institutions involved in the project/the contracting authority and the consultant.

•	Execution of the tasks according to a timeframe established by the project manager.

## Risks

Due to the nature of the actions to be implemented no special risk are foreseen to occur.  Risks that could affect the successful and timely completion of the project are:

Human Resources Risks:

•  The Consultant does not have sufficient time to manage in optimal conditions at all stages of the assignment.

•  Due to Covid-19 outbreak national restrictions will apply moving to the cross border area and in Gjirokaster.

•   Due to Covid-19 outbreak in field work will be restricted.

Technical Risks:

• Violation of the terms and conditions of the contract leading to delays in the assignment implementation.

# SCOPE OF THE WORK

## General

### Description of the assignment

This contract is part of the contractual obligations of the University ‘‘Eqrem Çabej’’ of Gjirokastra, as they arise from the contract of project CheeseCulT.

This contract is for the subset of the project CheeseCulT.

In particular, the contractor will be requested to provide support to the Contracting Authority “University ‘‘Eqrem Çabej’’, Gjirokastër for the implementation of WP1 “Project Management and Co-ordination”, WP 3 “Establishment of a traditional cheese route in CB area for raising gastronomic potential as a driving force for rural tourism development”, and WP5 “Innovative Actions (creation of Exhibition Centres & e-presence) for the establishment of the new cheese route in the CB area”.

### Geographical area to be covered

Gjirokastra Region

### Target groups

The target group of the Study will be potential stakeholders to be included in the project’s Cheese Route design, in the Albanian Cross Border Area (Gjirokastër).

- Dairy product SMEs and producers

- Tourism Stakeholders (Hotels and Other Accommodation enterprises as well as appropriate Restaurants and Other Culinary Establishments)

- Relevant Cultural Landmarks (physical and tangible in the form of cultural events) and Stakeholders

- Relevant Public Authorities (local, regional, national, European)

- Universities and R&D Actors and Research and Development bodies

- Unions, chambers and cooperatives

## Specific work

The specific work to be carried is presented below:

- Deliverable 1.3.2	Project Management and Coordination Activities

Specifically, the contractor will support the “Eqrem Çabej” University for the following tasks:

•	Coordination and monitoring of the Project’s progress in collaboration with the “Eqrem Çabej” University project team.

•	consulting and organizational support for the implementation of the Project’s physical object. Support in checking the data that document the proper completion of the physical object of the project

•	supporting the Project’s financial management and the process for the verification of expenses, collecting, checking the project’s expenses according to the Programme’s Implementation Guide.

•            supporting University ‘‘Eqrem Çabej’’ staff using MIS account.

•	supporting the preparation, the Project’s progress reports every six months, submission of the necessary administrative forms, etc.

•	supporting the preparation of tender documents in the context of the project.

•	supporting for the project’s check procedures by the competent Authorities and internal check procedures.

Deadline for performing the service is 30/11/2021 or until a new end-date of the CheeseCulT Project, if an extension is granted

- Deliverable 3.3.1	Diagnosis Study of sectors Linkage at Regional Level

Scope and objectives

Food or Culinary tourism has been under constant development and expansion over the previous decades, thus leading to the emergence of Food tourism studies that tend to focus on food destination, food tourists and hygiene issues, using both qualitative and quantitative analyses. According to these studies, gastronomic tourists are those tourists drawn into certain locations by their willingness to experience satisfaction in all senses but especially in terms of flavour. It has been suggested that the consumption of local cuisine increases the engagement to the local natural and cultural environment, offering a more complete experience to the visitor.

As local gastronomy is an integral part of the cultural, social, environmental, and economic history in every area, it tends to reflect the local lifestyle in the various regions. In addition, it operates as a bridge between tradition and contemporary lifestyle and culture. That said, local culinary traditions are not beyond the scope of innovation, especially when innovation is applied to provide greater value and thus increase local competitiveness. In that sense, local and regional food often provide added value to destinations, particularly in the cases of regions or areas that effectively promote their culinary traditions a major attraction and as a major part of the local identity.

The synergy cultivated between local food tradition and tourism can take various forms. Notable studied examples include:

Local Attraction. In this case, local gastronomy operates as an additional attraction for the touristic promotion of an area or region, and visitors are willing to travel there to taste specific products or dishes.

Component of the tourist product. In this case, the culinary experience is considered a part of the overall local experience and can take specific forms such as routes (wine or others).

Experience. This case is linked to the local attraction, but it refers to more specific experience such as unique restaurants or chefs.

Cultural Phenomenon. This is the case of the organizing of special, different or unique food festivals, usually linked to another cultural basis (religious or else).

The purpose of the study under discussion is to diagnose the conditions in the Albanian part of the Cross-Border Area, to identify the most suitable synergy between the primary sector, culinary tradition and tourism and to present the differentiation of the Cross-Border region, in order to incorporate the Cheese Route as a product in the regional policies and strategies. In this sense, gastronomy and its relation to tourism can become a key aspect in the analysis of the Cross-Border region as a tourist destination, supplementing the already present cultural elements.

Target Group

The target group of the Study will be potential stakeholders to be included in the project’s Cheese Route design.

Methodology Applied

The Study will collect data via desktop research focusing on the tourism capacity of the Albanian part of the CB area (based on official statistics) and on the linkage capacity between the dairy sector and tourism in the CB area. In addition, to supplement the desktop study on tourism, a primary survey will be conducted among tourism stakeholders (hotels, guesthouses, local restaurant) to identify specific aspects of local tourism value chains and their interest in the CheeseCulT project and the Cheese Route.

Desktop Study

The Desktop Study will be used for the collection of data to complement the general Diagnosis Study in order to identify the value chains of tourism in the Albanian area of the project and their local impact in economic and social terms. Furthermore, following a study on the various cases of developed synergies between agri-food primary sector and tourism, as well as a collection of good practices for linking tourism and primary sectors, in the form of policies, programs, activities, events, forums, initiatives or any other relevant and transferable form, the study will identify the type most suitable for the Project’s region and will propose actions and implementation steps to enhance the impact of the project.

Questionnaire Study

The purpose of the questionnaire is to explore the local interest in the Cheese Route and the ways each interested party could be interested to participate or to support to the Cheese Route activities, in addition to their viewpoints on any potential problems that could be encountered.

Target groups: The questionnaire study will be based on information from tourism and cultural stakeholders and local authorities.

Tools: Questionnaires will be used for the collection of data on tourism and cultural stakeholders and local authorities. These will be translated in Albanian to ensure the comprehension of content by the survey participants.

Analysis and Summary: Collected questionnaire data will be tabulated, analyzed and presented through descriptive statistics, including percentage values, average arithmetic and median value, together with a qualitative analysis.

ORGANIZATION OF THE STUDY

I- TOURISM SECTOR IN THE ALBANIAN CROSS BORDER AREA

-Characteristics of the Local Tourism Sector (tourism capacity, visits and overnight stays, tourism economic impact)

II- LINKAGE DEVELOPMENT BETWEEN AGROFOOD AND TOURISM SECTOR

-Linking Tourism and Primary Sectors (policies, programs, activities, events, forums, initiatives)

-Best Practices

III-QUESTIONNAIRE ANALYSIS

-Methodology of the survey

-Analysis of results

-Conclusions

IV- CONCLUSIONS

V- REFERENCES

Deadline for performing the service is 28/02/2021.

- Deliverable 5.3.1 Development of a Local Action Plan for Agro and Rural Tourism

Scope and objectives

The definition of a local scale tourism strategy, as reflected in the overall implementation of the CheeseCulT and in the vision prevailing among the stakeholders, is not sufficient by itself to implement it. An integral part of the strategy implementation refers to the identification of its objectives, each of which leads to specific outcomes through the production of outputs. The tool for the coherent operation of the above chain is the development of a Local Action Plan that will describe the activities needed to deliver the desired outputs.

Elaborating an Action Plan is an important step to prepare the implementation of a strategy for establishing and expanding links between the Agri-food Sector and Tourism Sectors. The Action Plan should be organized along with the strategic objectives, outcomes and outputs which will be achieved and should include budgeted actions, financial plan and a Monitoring and Evaluation process.

To this end, the contractor will follow the following task sequence:

- Current situation analysis on the development of the CheeseCulT Project and the Cheese Route development.

- Deciding on the mechanisms that will be used to achieve the goals

- Drafting the Local Action Plan

Methodology Applied

The Local Action Plan should operate as a roadmap for the implementation of the project-related Agrofood and Tourism Activities and a guide towards the solution of problems that have been already identified in previous WPs. Therefore, it should be detailed enough to be used regularly by individuals in charge of the operation, to control the actions, costs and timeline, to monitor and evaluate the implementation, to make necessary adjustments and to assess the results.

Tasks required in the preparation of the Local Action Plan include the following:

- Identifying and Listing of the main activities to be undertaken;

- Breaking up of broad activities into manageable tasks;

- Clarification of the sequence and dependencies between tasks;

- Establishment of Links with other official policy documents and strategies already in place;

- Estimation of start-up, duration and completion of the activities;

- Defining of Action Plan milestones

Budgeting of all designed activities is an element of particular importance and an essential element for the Local Action Plan. All described activities require to be carefully budgeted, in order to have an overview of the total costs. At the same time, it is also essential that each described activity also includes realistic proposals for its financing.

Taking these into account, the Local Action Plan budget will have to:

- Show the total current and future costs for the implementation of the activities included, or at the very least an accurate estimation;

- Specify the financing sources and the actors, authorities and stakeholders to be mobilized;

- Describe the main costs by category.

ORGANIZATION OF THE STUDY

The contents of the Local Action Plan will be adapted according to the results of the Diagnosis Studies and Consultations regarding the potential of Agritourism as a development tool in the Cross-Border Area. However, the overall structure to be followed in its drafting should be based on the following sections:

- SWOT analysis of Tourism and Agrofood Sectors Linkages in the Cross-Border Region;

- Description of Strategies to be implemented, incl. activities, links to official implemented policies in both countries and budgeting;

- Implementation Schedule.

Deadline for performing the service is 31/05/2021.

- Deliverable 5.3.4	Development of Cheese Agri – tourism network and Project External Evaluation

SCOPE AND OBJECTIVES

The final innovative element implemented within the framework of WP5 will be the final incorporation of all innovation elements to a Cheese Agri - tourism network, followed by the Project’s External Evaluation. As shown by the implemented activities, CheeseCulT has the potential of creating a sustainable network of stakeholders via the operation of the Cheese Route and the Agritourism Local Action Plan and support it with innovative elements such as the exchange of stakeholders’ visits, the e-cookbook and the Cheese Exhibition Centres. As all innovative activities will take place on both countries of the Cross-Border Area and will involve not only the collaboration between the project partners but also interested stakeholders from both sides, they create a basis for the establishment of a more permanent form of cooperation in the Agri-tourism sector.

In overall, the purpose of the said network development is to disseminate the work done during the project’s operation on the theme of Cheese (and other dairy products) Agritourism, highlight the added value of the project and thus attract interest and support in order to ensure the Cheese Route sustainability and to create a sustainable basis for the expansion of the project’s activities and scope in the post-project period, based on the activities described in the Local Action Plan.

As a final step of the project’s implementation, the External Evaluation is an essential step to ensure project quality, by providing independent and objective judgement on the progress of project work, assessing the overall quality and results and rating the project’s overall performance in terms of impact. In addition, the External Evaluation will investigate the effectiveness, efficiency of the project at stakeholder level during the implementation of training activities, during the demonstration of Cheese Road, and how they perceive their involvement in the innovative Cheese Road action.

METHODOLOGY APPLIED

The Development of the Cheese Agri - tourism network will take place through the incorporation of all WP5 elements. A key component for the Network Development will be the Local Action Plan, as it will provide the operational step by step approach for the stakeholders to expand the cooperation, they had during the Project’s implementation.

Related activities to be undertaken will have to include:

- the operation of the network between experts, travel agents, tourist entrepreneurs, producers & farmers or any other stakeholders;

- channelling & informing the results of the Cheese Route to the stakeholders;

- organizing the meetings in person and any other activities required (consultation sessions, support sessions etc.).

As to the Cheese Agri - tourism network, it will also include the development of a CB networking (online tool), to support the Cheese Route participants and other network stakeholders and to enhance the experience exchange between regional actors.

Regarding the External Evaluation of the Project, “Eqrem Çabej” University tasks involved include:

- Providing External Evaluator with project data.

- Supporting the External Evaluator during the evaluation procedures (questionnaires/interviews)

Following that the External Evaluator (Contractor) will examine:

- Whether all project deliverables have been produced and all described activities have been implemented.

- Whether the project indicators (and targets) as described in the Project Application Form have been reached.

The External Evaluator can also examine the CheeseCulT progress through the opinions of key stakeholders (consultations participants, training sessions participants, in order to have a more complete view of the project impact. For this evaluation procedure, the questionnaire and/ or the interview tool can be used (anonymously). The questionnaire template and/ or the interview guide will be developed by the evaluator.

As a final step, the External Evaluator will draft and deliver one Final External Evaluation Report for the CheeseCulT project.

Deadline for performing the service is 30/11/2021 or until a new end-date of the CheeseCulT Project, if an extension is granted

The contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. >

## Project management

### Responsible body

The Managing structure in the University ‘‘Eqrem Çabej’’ in Gjirokaster, for the purposes of this project, is as follows:

-	Scientific Research & International Relation Sector

-	The Finance Office

Responsible person, Mr. Sem Golemi

### Management structure

The Contracting Authority, University ‘‘Eqrem Çabej’’, Gjirokastra, and in that capacity it is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during project implementation.

The day-to-day operational project implementation will be also performed by University ‘‘Eqrem Çabej’’, Gjirokastra, which is responsible for implementation of project CheeseCulT financed under the IPA Cross-border Cooperation Programme “Greece-Albania 2014-2020”.

### Facilities to be provided by the contracting authority and/or other parties

The University ‘‘Eqrem Çabej’’ will provide the facilities of Scientific Research & International Relation Sector for meetings with the contractor.

# LOGISTICS AND TIMING

## Location

The operational base for the project will be set up in the offices of the Contracting Authority and in the offices of the Contractor.

## Start date & period of implementation of tasks

The intended start date is 30/10/2020 and the period of implementation of the contract will be 13 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

“Eqrem Çabej” University will monitor and adjust the timeline in coordination with other project partners and the situation restrictions from Covid -19 outbreak

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts have a crucial role in implementing the contract. These terms of reference contain the required key experts’ profiles. The tenderer shall submit CVs and statements of exclusivity and availability for the following key experts:

Key expert 1: Team leader

Qualifications and skills

- Bachelor and master’s degree (or equivalent) in Development studies, Management, Communications, Public Relations, or any other related fields.

- Proficient in Microsoft Office, content management systems and social media platforms.

- Very good skills in writing and speaking English.

- Be able to communicate clearly and effectively.

- Strong time-management and organizational skills.

- To be able to ensure confidentiality of project information.

Professional experience

- A minimum of three years of overall working experience in project management of EU projects.

- Similar experience in consultation with stakeholders and mapping activities during the last three years will be considered as an asset.

- Knowledge of cross border area will be considered as an asset.

- Similar experience in reporting to national auditing authorities as FLC or CFCU during the last three years will be considered as an asset.

Key expert 2. Expert on Tourism Sector Development

Qualifications and skills

- Bachelor and master’s degree (or equivalent) in business administration, economics, tourism, marketing management or any other related fields.

- Proficient in Microsoft Office, content management systems and social media platforms.

- Very good skills in writing and speaking English.

- Be able to communicate clearly and effectively.

- Strong time-management and organizational skills.

- To be able to ensure confidentiality of project information.

Professional experience

- A minimum of three years of overall working experience in Tourism Sector Development projects.

- Similar experience in Tourism Sector Development studies, during the last three years will be considered as an asset.

- Knowledge of cross border area will be considered as an asset.

Key expert 3. Expert on Regional Development

Qualifications and skills

- Bachelor and master’s degree (or equivalent) in business administration, economics, management or any other related fields.

- Proficient in Microsoft Office, content management systems and social media platforms.

- Very good skills in writing and speaking English.

- Be able to communicate clearly and effectively.

- Strong time-management and organizational skills.

- To be able to ensure confidentiality of project information.

Professional experience

- A minimum of three years of overall working experience in Regional Development projects.

- Similar experience in Regional Development studies, during the last three years will be considered as an asset.

- Knowledge of cross border area will be considered as an asset.

Key expert 4. Expert on Agro food technology

Qualifications and skills

- Bachelor and master’s degree (or equivalent) in Agricultural Sciences on or any other related fields.

- Proficient in Microsoft Office

- Good skills in writing and speaking English.

- Be able to communicate clearly and effectively.

- Strong time-management and organizational skills.

- To be able to ensure confidentiality of project information.

Professional experience

- A minimum of three years of overall working experience.

- Similar experience in Agro food technology, during the last three years will be considered as an asset.

- Knowledge of cross border area will be considered as an asset.

The Consultants must be independent and free from conflicts of interest in the responsibilities he/she takes on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original:

Draft final report of maximum 25 pages (main text, excluding annexes). This report shall be submitted no later than one month before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 15 days after receipt of comments on the draft final report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Specific performance measures to measure the progress towards achieving the expected results will be quantitative measures of quantity such as the number of reports/ deliverables that have been delivered compared to the project timetable.

## Special requirements

Any information and publicity actions should follow the recommendation of the “Information & Publicity Project Partners Guidebook” available in the website of the Managing Authority (see http://www.greece-albania.eu)